## Burndown Chart
Payment Use Case
| Tasks | Total Hours | Day1 | Day2 | Day3 | Day4 | Day5
1 | Create Instantiable Classes | 5 | 2 | 0 | 1 | 0 | 2
2 | Create App Classes | 3 | 3 | 0 | 0 | 0 | 0
3 | Create GUI interface | 5 | 3 | 0 | 1 | 0 | 1
4 | Create Test Cases | 6 | 2 | 0 | 4 | 0 | 0
5 | Unit/Component Testing | 7 | 0 | 1 | 0 | 1 | 5
6 | Perfomace Testing | 7 | 0 | 1 | 0 | 1 | 5
7 | UAT Testing | 11 | 1 | 0 | 0 | 3 | 7
|  | Total Hours | Day1 | Day2 | Day3 | Day4 | Day5
| Actual Results | 44 | 33 | 31 | 25 | 20 | 0
| Estimation | 40 | 32 | 24 | 16 | 8 | 0
| Variance | 4 | 1 | 7 | 9 | 12 | 0